## Slide 1: Ch.8 Project Quality Management Pages 226 - 254 of PMBOK Guide 5th Edition

## Slide 2: Ch.8 Project Quality Management
Quality Management includes creating and following policies and procedures to ensure that a project meet the defined needs (from the customer’s perspective).
Quality definitions and concepts
Prevention is the better than control. Do it right the first time. Zero Defects is the goal of quality. Philip Crosby
Quality is defined as the degree to which the project fulfills requirements. Or quality means fitness for use. Joseph Juran
Quality relates to continues improvement of people and procedures. Kaizan
Quality relates to processes and procedures not people. Or quality is the management’s problem. Management needs to provide the procedures and resources for the employees to produce quality product. Edwards Deming
Quality Management is applying the processes that will ensure the project will meet the needs for which it was undertaken
Quality Vs Grade Vs Gold Plating?
Quality is the degree to which
a set of inherent characteristics fulfill requirements” (ISO 9000)

## Slide 3: Ch.8 Processes of Quality Management
8.1 Plan Quality Management
The process of identifying project’s quality requirements and how the these requirements will be met.
8.2 Perform Quality Assurance
Here we apply the quality requirements and audit results from quality control process to ensure proper procedures are applied.
8.3 Control Quality
In this process we measure and record quality requirements to ensure quality is achieved and recommend changes if needed.

## Slide 4: 8.1 Plan Quality Management: ITTOs
1. Project Management Plan
2. Stakeholder register
3. Risk Register
4. Requirements documentation
6. EEF/OPA
1. Cost benefit analysis
2. Cost of Quality (CoQ)
3. Benchmarking
4. Design of experiments
5. Statistical sampling
6. Additional quality planning tools
7. Meetings
8. Seven basic quality techniques
1. Quality management plan
2. Quality metrics
3. Quality checklists
4. Process improvement plan
5. Project document updates
Input
Tools & Techniques
Output
The process of identifying quality requirement and/or standards for the project and product and documenting how the project will demonstrate compliance.
  What is quality for this project ? How will we ensure it?

## Slide 5
8.1.1.1 Project Management Plan
8.1.1.2 Stakeholder Register
Scope Baseline: The Scope Statement of Scope Baseline gives us important information related to project quality.
It tells us about the stakeholder that are concerned with quality aspect of the project
Other elements of the PMP used for planning the quality are the Schedule Baseline and Cost Baseline
The scope statements contains project deliverables and their acceptance criteria
8.1 Plan Quality Management: Inputs

## Slide 6
8.1.1.3 Risk Register
8.1.1.5 EEF/OPA
8.1.1.4 Requirements Documentation
It includes requirements about quality of the product.
Government Regulations, Industry Standards, Policies and Procedures, Historical Information etc
It contains information about the risks that may affect the quality of the project
It will help us better plan Control Quality Process
8.1 Plan Quality Management: Inputs

## Slide 7
8.1.2.1 Cost Benefit Analysis
8.1.2.2 Cost of Quality
We maintain quality to have less rework, lower costs, higher productivity, and higher costumer satisfaction
Balancing between the cost conformance and nonconformance
In Cost Benefit Analysis we compare benefits versus the cost of achieving quality
8.1.2 Plan Quality Management: T&Ts
Should be less than
<

## Slide 8
8.1.2.3 Seven basic quality tools
The 7QC tools as they are called, are used in within the context of Plan-Do-Check-Act (PDCA) cycle to solve quality related problems
8.1.2 Plan Quality Management: T&Ts
The whole process is conducted in brainstorming sessions. The steps involved are as follow:
  Identify the problem.
  Work out the major factors involved.
  Identify possible causes.
  Analyze your diagram
You can also add factors such as Environment, and Materials or any other factor deemed related.
Major causes are further investigated. At the end the whole diagram is analyzed and possible cause or causes are identified.
1. Cause-and-effect Diagram: Cause-and-effect diagram or fishbone diagram or Ishikawa diagram is used to find possible causes of a problem or failure

## Slide 9
8.1.2.3 Seven basic quality tools
The 7QC tools as they are called, are used in within the context of Plan-Do-Check-Act (PDCA) cycle to solve quality related problems
8.1.2 Plan Quality Management: T&Ts
2. Flowcharts: Also called process maps, because flowcharts display sequence of steps. The flowchart transforms one or more input to one or more outputs.

## Slide 10
8.1.2.3 Seven basic quality tools
The 7QC tools as they are called, are used in within the context of Plan-Do-Check-Act (PDCA) cycle to solve quality related problems
8.1.2 Plan Quality Management: T&Ts
2. Flowcharts: Also called process maps, because flowcharts display sequence of steps. The flowchart transforms one or more input to one or more outputs.

## Slide 11
8.1.2.3 Seven basic quality tools
The 7QC tools as they are called, are used in within the context of Plan-Do-Check-Act (PDCA) cycle to solve quality related problems
8.1.2 Plan Quality Management: T&Ts
2. Flowcharts: Also called process maps, because flowcharts display sequence of steps. The flowchart transforms one or more input to one or more outputs.

## Slide 12
8.1.2.3 Seven basic quality tools
The 7QC tools as they are called, are used in within the context of Plan-Do-Check-Act (PDCA) cycle to solve quality related problems
8.1.2 Plan Quality Management: T&Ts
3. Checksheet: Used to collect useful data about a problem or its attributes when performing inspections.

## Slide 13
8.1.2.3 Seven basic quality tools
The 7QC tools as they are called, are used in within the context of Plan-Do-Check-Act (PDCA) cycle to solve quality related problems
8.1.2 Plan Quality Management: T&Ts
4. Pareto Diagrams: Pareto thought 80 percent of the quality related problems are effects of 20 percent of the causes.

## Slide 14
8.1.2.3 Seven basic quality tools
The 7QC tools as they are called, are used in within the context of Plan-Do-Check-Act (PDCA) cycle to solve quality related problems
8.1.2 Plan Quality Management: T&Ts
In this example the distribution of data is based on a bell curve. The name comes from it shape which like a bell.
In this example the highest frequency of the measurement was between 20 and 22. The occurrence/frequency for this measurement is close to 28 times.
5. Histograms: Histograms are special types of bar charts that show central tendency, dispersion, and shape of statistical distribution.

## Slide 15
8.1.2.3 Seven basic quality tools
The 7QC tools as they are called, are used in within the context of Plan-Do-Check-Act (PDCA) cycle to solve quality related problems
8.1.2 Plan Quality Management: T&Ts
Control Charts are also used to determine if a management process is in control by measuring factors like schedule or cost variances, or the frequency of changes into scope etc.
1.Upper control limit
2. Lower control limit
3. Out of control
5.Specification limit: is point determines by customer, not calculated based on control chart
4. Rule of seven: Out of control if 7 measurements are above or below the mean
6. Normal and expected variation
Usually 3 or 6 sigma
6. Control Charts: Control Charts are used to know whether a process is stable or has the desired performance. Control Charts are used for repetitive process e.g manufacturing

## Slide 16
8.1.2.3 Seven basic quality tools
The 7QC tools as they are called, are used in within the context of Plan-Do-Check-Act (PDCA) cycle to solve quality related problems
8.1.2 Plan Quality Management: T&Ts
Once we know that there is a correlation between the two variables then we can estimate how changes to independent variable can result in a change in the dependent variable.
Graph a, b, c, and d show different correlation that may exist between two variables. For example in graph b the Y axis may show number of iteration and X axis may show number of bugs found in the software.
7. Scatter Diagram: Scatter Diagram is used to check for correlation between two variables

## Slide 17
8.1.2.4 Benchmarking
8.1.2.5 Design of Experiment
Comparing the project in hand with similar projects completed in the past in order to identify best practices, and generate new ideas.
DOE is used to identify factors that can influence different variables of the product or process
DOE is used in Plan Quality Management to determine the number and type of tests needed to achieve the required quality
8.1 Plan Quality Management: T&Ts
In DOE we can change multiple variables at a time. In doing so we find optimal condition for product or process.
Imagine the example on the left is about producing brick under different conditions or with an input of different proportions of the materials
Once we know that various factors can influence our product in various ways, we will develop tests or quality check list for them.

## Slide 18
8.1.2.6 Statistical Sampling
8.1.2.7 Other Quality Tools
Statistical Sampling refers to choosing few items as a sample from a larger group of items.
Brainstorming: Used for generating ideas
Here we do not do the actual sampling but decide on how we will do how sampling in the coming quality processes
This will help us in correctly determining the cost of quality.
Force Field Analysis: Diagrams of forces for and against change
Nominal Group Technique: In this technique we vote for ideas to be further discussed by a larger group of people
Quality Control and Management Tools: This tools will be explained in the next process.
8.1.2.8 Meetings
Quality related meetings are attended by the project sponsor, project management, selected project team member, selected stakeholders, team members that are responsible for quality of the project.
8.1 Plan Quality Management: T&Ts

## Slide 19: 8.1 Plan Quality Management: T&Ts
Below is an example of force-field diagram

## Slide 20
8.1.3.1 Quality Management Plan
8.1.3.2 Process Improvement Plan
Quality management plans explains how organizations quality policies will be implemented.
Depending on the project, the plan can be very detailed or simple.
This plan details the steps that will help as in improving various process in our project.
Process Improvement Plan is part of the PMP
The plan is implemented in the QA and QC processes
8.1 Plan Quality Management: Outputs
Areas included in the Process Improvement Plan are as follow:
Process Boundaries: The propose of the process, the start and end date, the inputs and outputs of the process
Process Configuration: Graphical depiction of the process
Process Metric: Used for measuring process efficiency
Targets for Improved Performance: Targets for improvement

## Slide 21
8.1.3.3 Quality Metrics
8.1.3.4 Quality Checklists
Based on the product requirements a checklist is developed
It describes the project or product attributes and how the quality control process will measure it.
8.1.3.5 Document Update
Risk Register, Requirement Traceability Matrix, and WBS dictionary are updated
Examples of quality metrics are finishing the project within the budget and time, the frequency of defects, failure rate, etc.
The metrics and the tolerance level for variation is set in Plan Quality
The attributes are measured in control quality
The checklist will list the steps to be followed to achieve the desired quality for the product
The checklist should also contain the product requirements
8.1 Plan Quality Management: Outputs

## Slide 22
8.1.3.3 Quality Metrics
It describes the project or product attributes and how the quality control process will measure it.
Examples of quality metrics are finishing the project within the budget and time, the frequency of defects, failure rate, etc.
The metrics and the tolerance level for variation is set in Plan Quality
The attributes are measured in control quality
8.1 Plan Quality Management: Outputs
Metric | Standard | Frequency | Report
Tensile Strength | ≥500 MPa | Per prototype | Monthly Quality Management Review (QMR)
Shear Strength | ≥ 375 MPa | Per prototype | Monthly QMR
Customer Satisfaction | 8/10 or higher with no individual score below 7 | Per prototype | Monthly QMR
Material Waste | < 1% based on total material used per tool | Per prototype | Monthly QMR
Product Defect Rate | < 1 out of 500 | Per production of 500 tools | As achieved

## Slide 23
8.1.3.3 Quality Metrics
It describes the project or product attributes and how the quality control process will measure it.
Examples of quality metrics are finishing the project within the budget and time, the frequency of defects, failure rate, etc.
The metrics and the tolerance level for variation is set in Plan Quality
The attributes are measured in control quality
8.1 Plan Quality Management: Outputs
Tactical Measure | Question Answered | Sample Indicator
Time | How are we doing against the schedule? | Schedule Performance Index (SPI) = Earned Value ÷ Planned Value
Cost | How are we doing against the budget? | Cost Performance Index (CPI) = Earned Value ÷ Actual Cost
Resources | Are we within anticipated limits of staff-hours spent? | Amount of hours overspent per software iteration
Scope | Have the scope changes been more than expected? | Number of Change Requests
Action Items | Are we keeping up with our action item list? | Number of action items behind schedule for resolution

## Slide 24: 8.2 Perform Quality Assurance: ITTOs
1. Quality Management Plan
2. Process Improvement Plan
Quality metrics
3.Quality control measurement
4. Project Documents
1. Quality Management and Control Tools
2. Quality audits
3. Process analysis
1.Change Requests
2. Project management plan updates
3. Project document updates
4. OPA updates
Input
Tools & Techniques
Output
In Quality Assurance we ensure the proper quality related procedures are followed. We do this by auditing the quality requirements and results received from Quality Control Process

## Slide 25
8.2 Perform Quality Assurance: Data Flow Diagram

## Slide 26: 8.2.1 Perform Quality Assurance: Inputs
8.2.1.1 Quality Management Plan
It contains plan for quality assurance and process improvement
8.2.1.2 Process Improvement Plan
This will tell us about the project’s process improvement plan which needs to be aligned with quality assurance process.
8.2.1.3 Quality Metrics
This will tells what we need to measure and what are the allowable variation for our measurements.
8.2.1.4 Quality Control Measurements
These are the measurements taken in the Control Quality Process
The measurements are used fed back to Quality Assurance in order to evaluate the effectiveness of quality assurance procedures/processes

## Slide 27: 8.2.2 Perform Quality Assurance: T&Ts
8.2.2.1 Quality Management and Control Tools
Beside other available tools, in quality assurance we use all the tools that are used in Plan Quality Management and Control Quality Processes
Affinity Diagram……?
  Classifying large number of ideas into groups

## Slide 28: 8.2.2 Perform Quality Assurance: T&Ts
8.2.2.1 Quality Management and Control Tools
In Quality Assurance we use tools used in Plan Quality Management and Control Quality Processes plus the tools below
Process Decision Program Chart (PDPC)
PDPC systematically identifies what might go wrong in a plan under development.
1. You divided in and subdivide a complex plan into more simple steps
3. You identify possible problems that will hinder implementing the plan.
4. You identify possible problems that will hinder implementing the plan.
5. You put O in front of the solutions that are practical and you put X in front of the solutions that are not practical
At the end you either change your plan where there is no practical solution or prepare yourself accordingly

## Slide 29: 8.2.2 Perform Quality Assurance: T&Ts
8.2.2.1 Quality Management and Control Tools
In Quality Assurance we use tools used in Plan Quality Management and Control Quality Processes plus the tools below
Interrelationship Digraph
It is used for problem identification and problem solving in complex systems
Interrelationship Digraph is usually used after Case-and-effect diagram, idea mind mapping, affinity diagram.
Here we construct how different problems are related to each other.
After constructing the Digraph we start interpreting it.
Interpretation can be as:
1. An item with large number of outputs e. g “Poor Scheduling Practice” can be cause of many effect
2. An item with large number of inputs e. g “Poor Scheduling of Trucker” can be source of Quality metrics.

## Slide 30: 8.2.2 Perform Quality Assurance: T&Ts
8.2.2.1 Quality Management and Control Tools
In Quality Assurance we use tools used in Plan Quality Management and Control Quality Processes plus the tools below
Tree Diagram
It is used to show how the general plan is related to specific parts e. g in WBS. Also it is used to see the results of different decision that we might be making in our project.
Through Tree Diagram we learn how different decision can affect our project. How doing a process in different way can have an effect on our product. Or
Tree Diagram will help us in better understanding of the situation and our future decisions.

## Slide 31: 8.2.2 Perform Quality Assurance: T&Ts
8.2.2.1 Quality Management and Control Tools
In Quality Assurance we use tools used in Plan Quality Management and Control Quality Processes plus the tools below
Network Diagram: Network Diagram shows how activates are connected to each other. It helps us understand when are we going to apply our quality procedures
Matrix Diagram: The matrix diagram shows relationship between factors, causes, and objectives.

## Slide 32: 8.2.2 Perform Quality Assurance: T&Ts
8.2.2.2 Quality Audits
Quality audits are independent reviews of the quality processes and procedures of an organization.
8.2.2.3 Process Analysis
In Process Analysis we implement the plan outlined as “Process Improvement Plan” which was an output to Plan Quality Management process
Quality audits can done randomly or on scheduled bases and can be carried externally or internally.
Quality audits can confirm implementation of approved changes, corrective actions, preventive action, or defect repairs.
Here we use root-cause analysis which will help us identify problems in our processes and take preventive actions.

## Slide 33
8.2.3.1 Change Requests
8.2.3.2 Project Management Plan updates
Quality Management Plan, Scope Management Plan, Schedule Management Plan, and Cost Management Plan are updated.
Change requests related to corrective, preventive, and defect repair are made.
8.2.3.3 Project Document Update
Audit Reports, Training Plans, and Process Documentation are updated.
8.2.3.4 OPA Updates
Organization quality standards and quality management systems are updated
8.2.3 Perform Quality Assurance: Outputs

## Slide 34: 8.3 Control Quality: ITTOs
1. Project Management Plan
2. Quality Metrics
3. Quality Checklists
4. Work Performance Data
5. Approved Change Requests
6. Deliverables
7. Project Documents
8. OPA
1. Seven Basic Quality Tools
2. Statistical Sampling
3. Inspection
4. Approved change requests review
1. Quality Control Measurements
2. Validated changes
3. Verified deliverables
4. Work Perf Info
5. Change Requests
6. Project Doc updates
7. Project Mangtm Plan updates
8. OPA updates
Input
Tools & Techniques
Output
In Control Quality we monitor and record results from executing the quality activities. We do this mainly for two reason:
1. To identify the cause for poor quality and request change, and 2 Validate the deliverables to be accepted by stakeholders.

## Slide 35: 8.3 Control Quality
More Quality Concepts
Prevention Vs Inspection
Prevention is about keeping errors out of process, and Inspection is about keeping errors out of hands of the customer
Tolerance Vs Control Limits
Tolerance is a specified range of acceptable results, and Control Limits is about specifying boundaries for a stable process
Attribute Sampling Vs Variable Sampling
The result of an attribute either conforms or does not conforms, and the result of variable is on continue scale with a degree conformity

## Slide 36
8.3.1.1 Project Management Plan
8.3.1.2 Quality Metrics
It describes project or products attributes and how they will be measured.
Quality Management Plan of the Project Management Plan is used
Some examples are: Function Points, Mean Time Between Failure (MTBF), and Mean Time to Repair (MTTR)
8.3.1 Control Quality: Inputs
Function Points: In IT, Function Points are used a unit of measurement to count the number of function an information system providing to a business. The same as we use hours to measure time.
MTBF: it shows the reliability of product. It specifies the time between two failures that a product can have. For example an hard disk will have a failure after 300,000 hours.
MTTR: is the average amount of time a device or product will need to be repaired for a given failure.

## Slide 37
8.3.1.3 Quality Checklists
8.3.1.4 Work Performance Data
The data gather from actual which can include planned Vs actual schedule performance, cost performance and technical performance
A list that will help us verify that our work will fulfill the requirements of the product.
8.1.3.5 Approved Change Requests
The changes requested may include defect repairs which needs to quality controlled and verified
8.3 Control Quality: Inputs

## Slide 38
8.3.1.6 Deliverables
8.3.1.7 Project Documents
Agreements, quality audit documents, training plans and their assessment, process documentation
Deliverables are validated in Control Quality process.
8.3.1.8 OPA
Organization’s quality policies, defect reporting procedure, and communication policy
8.3 Control Quality: Inputs

## Slide 39
8.3.2.1 The Seven Basic Quality Tools
8.3.2.2 Statistical Sampling
As defined in the Quality Management Plan, samples are selected and tested
These were explained in 8.1.2.3
8.3.2.3 Inspection
Inspection refers to the examination of the product in order to determine whether it according to the documented standards.
Inspection can be related to a single activity, part of product, or the whole product.
Inspection are also called, review, peer reviews, audits, or walkthroughs.
Inspections are also used to validate defect repairs.
8.3.2.4 Approved Change Request Reviews
All the approved change requests are reviewed to verify they are implemented as approved.
8.3.2 Control Quality: T&Ts

## Slide 40
8.3.3.1 Control Quality Measurements
8.3.3.2 Validated Changes
When a product is changed or repaired after approved changes are implemented, the change or repair is validated in Control Quality process.
Control Quality Measurements are the results of Control Quality process
8.3.3.3 Verified Deliverables
Of the goals of Control Quality is to verify the correctness of deliverables
This is done using Review Approved Change Requests technique
The change or repaired done is either validated or rejected
Thus deliverables are either verified or rejected for repair or change
The verified deliverables becomes input to Validate Scope process where they are formally accepted or rejected.
These are input to Perform Quality Assurance process
8.3.3 Control Quality: Outputs

## Slide 41
8.3.3.4. Work Performance Information
8.3.3.5 Change Requests
Change requests in the form of rework, repair, change to management plan etc are made.
WPI is performance related data that is output to many monitoring and controlling processes
8.3.3.6 Project Management Plan Updates
Quality Management Plan, and
In this process WPI will show projects achievement of the requirements, information about rejections and reasons for the rejections, also rework required and need for change in quality processes
Process Improvement Plans might be updated
8.3.3 Control Quality: Outputs

## Slide 42
8.3.3.7 Project Document Updates
8.3.3.8 OPA updates
Completed Checklists: When checklists are used, the documented checklist becomes part of project document and OPA
Agreements, quality audit documents, training plans and their assessment, process documentation
Lesson Learned Doc: The causes of variances, the reasoning behind the corrective action selected, and other types of lessons learned stored as OPA
8.3.3 Control Quality: Outputs

## Slide 43
Exercise
No | Situation | What tool/technique is used | Which process it is
1 | Looking at other similar projects |  | 
2 | Measuring 4 out of 250 doors |  | 
3 | Identifying factors that influence particular variables of a product or process |  | 
4 | Finding the most frequent problems |  | 
5 | Comparing the cost of quality improvement against the benefits that it can bring |  | 
6 | Determining what will be an acceptable range to define a stable performance |  | 

## Slide 44
Exercise
No | Situation | Technique used | Which process it is
1 | Looking at other similar projects | Benchmarking | Plan Quality Management
2 | Measuring 4 out of 250 doors | Statistical Smapling | Control Quality
3 | Identifying factors that influence particular variables of a product or process | Design of experiments | Plan Quality Management
4 | Finding the most frequent problems | Pareto diagram | Perform Quality Assurance
5 | Comparing the cost of quality improvement against the benefits that it can bring | Cost-benefit analysis | Plan Quality Managmeent
6 | Determining what will be an acceptable range to define a stable performance | Control Charts | Plan Quality Management

## Slide 45
Exercise
No | Situation | What tool/technique is used | Which process it is
7 | Comparing what was done to what was documented to be done |  | 
8 | Graphically representing a process to determine where a process that is achieving low-quality results might be failing |  | 
9 | Taking measurements and comparing them to the upper and lower thresholds of variance |  | 
10 | Collecting data about defects discovered during inspection |  | 
11 | Analyzing a graphic with an organized series of lines displaying issues that might have led to a defect to examine if the proper process was followed |  | 
12 | Collecting many data point to look at the pattern of relationships or correlation between two variable |  | 

## Slide 46
Exercise
No | Situation | Technique used | Which process it is
7 | Comparing what was done to what was documented to be done | Checksheet | Control Quality
8 | Graphically representing a process to determine where a process that is achieving low-quality results might be failing | Flowcharting | Control Quality
9 | Taking measurements and comparing them to the upper and lower thresholds of variance | Control chart | Control Quality
10 | Collecting data about defects discovered during inspection | Checksheet | Control Quality
11 | Analyzing a graphic with an organized series of lines displaying issues that might have led to a defect to examine if the proper process was followed | Cause and effect diagram | Perform Quality Assurance
12 | Collecting many data point to look at the pattern of relationships or correlation between two variable | Scatter diagram | Control Quality